CropSense

AI-Powered Crop Pest & Disease Detection

Project Development Outline & Team Task Assignment

| Project CropSense | Challenge Ghana AI Innovation Challenge 2026 | Domain Agriculture | Submission Deadline 1st July 2026 |
| --- | --- | --- | --- |

Team Member Key

| Data Scientist (Lead) | Software Developer | Electronics Engineer | CAD / Prototyping | All Team Members |
| --- | --- | --- | --- | --- |

# Development Timeline Overview

| Stage | Title | Duration | Primary Owner(s) |
| --- | --- | --- | --- |
| Stage 1 | Project Setup & Data Preparation | Week 1–2 | Data Scientist, Electronics Eng., CAD |
| Stage 2 | AI Model Development & Training | Week 3–5 | Data Scientist, Software Developer |
| Stage 3 | Mobile App Development | Week 5–8 | Software Developer, Data Scientist |
| Stage 4 | Embedded Device Development | Week 5–9 | Electronics Eng., CAD, Software Dev. |
| Stage 5 | Integration, Testing & Refinement | Week 9–10 | All Team Members |
| Stage 6 | Submission & Summit Preparation | Week 10–12 | All Team Members |

Stage 1 ¦ Project Setup & Data Preparation Week 1 – 2

Objective: Establish the project foundation: set up the shared GitHub repository, prepare and pre-process the crop pest dataset, and align all team members on tools and workflow.

| Task | Owner | Details | Timeline |
| --- | --- | --- | --- |
| GitHub repository setup & project structure | Software Developer | Create repo, define folder structure (data/, models/, app/, device/, cad/), configure README and branching strategy | Day 1–2 |
| Dataset download, inspection & EDA | Data Scientist | Download dataset from Mendeley, inspect class distribution across 22 classes, identify imbalances, document findings | Day 1–4 |
| Data pre-processing pipeline | Data Scientist | Resize all images to 224x224, normalise pixel values, split into train/validation/test (70/15/15), write reusable preprocessing scripts | Day 3–6 |
| Data augmentation scripts | Data Scientist | Implement augmentation (rotation, flip, brightness, contrast, zoom) using TensorFlow ImageDataGenerator | Day 5–7 |
| Hardware component procurement list | Electronics Engineer | Research and document Raspberry Pi Zero 2W, OV5647 camera module, LCD display, Li-Po battery, and supporting components; prepare procurement order | Day 1–5 |
| CAD concept sketches for device enclosure | CAD / Prototyping | Sketch initial form factor for handheld scouting device; define rough dimensions to accommodate Pi + camera + display + battery | Day 3–7 |

Stage Deliverables:

- GitHub repository live with all team members onboarded

- Cleaned and split dataset ready for model training

- Data augmentation scripts committed and tested

- Hardware procurement list finalised

- Initial device concept sketches completed

Stage 2 ¦ AI Model Development & Training Week 3 – 5

Objective: Train, evaluate, and benchmark the CNN classification model. Select the best architecture for dual deployment (mobile + embedded). Export to TensorFlow Lite.

| Task | Owner | Details | Timeline |
| --- | --- | --- | --- |
| Baseline model training (MobileNetV2) | Data Scientist | Implement transfer learning from ImageNet pretrained MobileNetV2; fine-tune on crop dataset; log accuracy, loss, confusion matrix | Day 1–5 |
| Benchmark model training (EfficientNet-Lite) | Data Scientist | Train EfficientNet-Lite0 and Lite2 variants; compare against MobileNetV2 on accuracy, inference speed, and model size | Day 5–10 |
| Model evaluation & selection | Data Scientist | Evaluate all models on test set; generate per-class precision/recall/F1; select final model based on accuracy vs. latency trade-off | Day 10–12 |
| TensorFlow Lite export & quantisation | Data Scientist + Software Developer | Convert selected model to .tflite format; apply INT8 post-training quantisation; verify accuracy loss is within 1%; test inference on test images | Day 12–15 |
| Treatment recommendation database | Software Developer | Create JSON lookup table mapping each of the 22 disease/pest classes to a concise treatment recommendation in English and Twi | Day 8–12 |

Stage Deliverables:

- Trained model achieving >= 92% test accuracy on 22-class dataset

- Benchmark comparison table committed to repository

- Final .tflite model file (quantised) committed to repository

- Treatment recommendation JSON database (English + Twi)

Stage 3 ¦ Mobile App Development (Project 1) Week 5 – 8

Objective: Build the CropSense mobile application in .NET MAUI. Integrate the TFLite model for on-device inference. Implement camera capture, result display, and offline treatment recommendations.

| Task | Owner | Details | Timeline |
| --- | --- | --- | --- |
| .NET MAUI app scaffold & UI design | Software Developer | Set up .NET MAUI project in Visual Studio; design UI screens (home, camera capture, result, settings) using XAML; implement English/Twi language toggle via resource files | Day 1–6 |
| TFLite model integration into app | Software Developer + Data Scientist | Bundle .tflite model in .NET MAUI raw assets; integrate TensorFlow.Lite NuGet package; write image pre-processing pipeline matching training parameters using SkiaSharp | Day 5–10 |
| Camera capture & image input flow | Software Developer | Implement live camera capture and gallery upload; add image cropping/resizing to 224x224 before inference | Day 6–10 |
| Result screen & recommendation display | Software Developer | Display detected disease name, confidence score, crop type, and treatment recommendation; show healthy/warning/critical colour badge | Day 10–14 |
| Offline functionality & app testing | Software Developer | Verify all features work without internet; test on Android and iOS devices of varying specs; fix crashes and UI issues; measure inference time | Day 14–18 |
| App UX review & Twi localisation check | Data Scientist | Review UI flow from a farmer's perspective; verify Twi translations are accurate; suggest UX improvements | Day 15–18 |

Stage Deliverables:

- Working .NET MAUI app running on Android and iOS

- On-device inference under 2 seconds on mid-range phones

- Disease result screen with treatment recommendation in English and Twi

- Fully offline — no internet dependency confirmed

Stage 4 ¦ Embedded Device Development (Project 2) Week 5 – 9

Objective: Design and build the CropSense handheld embedded scouting device. 3D-print the enclosure, wire the hardware, and deploy the TFLite model on Raspberry Pi with a Python inference pipeline.

| Task | Owner | Details | Timeline |
| --- | --- | --- | --- |
| Device enclosure CAD design | CAD / Prototyping | Design full 3D model of handheld enclosure in Fusion 360; include camera aperture, display window, button cutouts, battery slot, and ventilation; export .STL files | Day 1–8 |
| 3D printing & enclosure assembly | CAD / Prototyping | Print enclosure in PLA/PETG; test fit of all components; iterate and reprint if needed; sand and finish for presentation | Day 8–14 |
| Hardware wiring & circuit assembly | Electronics Engineer | Wire Raspberry Pi Zero 2W to OV5647 camera, 2-inch LCD display, status LEDs, push button, and Li-Po battery with protection circuit | Day 1–8 |
| Power management & battery circuit | Electronics Engineer | Implement TP4056-based Li-Po charge circuit; add power switch; test 6-hour runtime target; add low-battery LED indicator | Day 6–12 |
| Raspberry Pi OS setup & TFLite runtime | Software Developer | Flash Raspberry Pi OS Lite; install TFLite Runtime, OpenCV, and Pillow; deploy model and test inference on device | Day 3–8 |
| Python inference firmware | Software Developer + Electronics Engineer | Write main.py: button-triggered capture, image pre-processing, TFLite inference, result display on LCD, LED colour output (green=healthy, red=diseased), audio beep | Day 8–15 |
| Field simulation testing | All team members | Simulate outdoor use: test under natural light, different backgrounds, partial leaf coverage; measure inference time on device; fix edge cases | Day 15–18 |

Stage Deliverables:

- Printed and assembled device enclosure

- Fully wired and powered hardware prototype

- Python firmware deployed and running on Raspberry Pi

- On-device inference confirmed under 3 seconds

- CAD files (.STL and Fusion 360) committed to repository

Stage 5 ¦ Integration, Testing & Refinement Week 9 – 10

Objective: Bring both projects together for final integration testing. Fix bugs, improve accuracy on edge cases, and ensure both deliverables are demo-ready for the Summit.

| Task | Owner | Details | Timeline |
| --- | --- | --- | --- |
| End-to-end mobile app testing | Software Developer + Data Scientist | Run full test suite: 50+ real leaf photos across all 22 classes; log accuracy, false positives, and UI issues; patch model or app as needed | Day 1–5 |
| End-to-end device testing | Electronics Engineer + Software Developer | Run device through 100+ capture-infer cycles; test battery life; stress test for thermal performance; fix hardware faults | Day 1–5 |
| Model fine-tuning on failure cases | Data Scientist | Collect and retrain on images that were mis-classified during integration testing; re-export updated .tflite; redeploy to both platforms | Day 3–7 |
| GitHub repository clean-up & documentation | Software Developer | Write README with setup instructions, model performance summary, and demo guide; ensure all scripts are reproducible; add licence file | Day 5–8 |
| Final device assembly & finish | CAD / Prototyping + Electronics Engineer | Final enclosure fit check; label device; ensure clean cable routing inside casing; prepare carry case for summit transport | Day 6–10 |

Stage Deliverables:

- Final tested .NET MAUI app and device firmware committed

- Updated .tflite model with improved accuracy on edge cases

- Complete GitHub repository with documentation

- Summit-ready physical device prototype

Stage 6 ¦ Competition Submission & Summit Preparation Week 10 – 12

Objective: Prepare and submit the Technical Abstract by 1st July 2026. Design the poster for Summit Day. Prepare and rehearse the live 10-15 minute pitch.

| Task | Owner | Details | Timeline |
| --- | --- | --- | --- |
| Technical Abstract writing | Data Scientist + Software Developer | Write the 1-2 page technical abstract covering: problem statement, dataset, methodology, results, impact, and team. Submit via challenge portal by 1st July 2026 | Day 1–5 |
| Technical Abstract review | All team members | All team members review and approve abstract before submission; check accuracy of results, methodology descriptions, and team details | Day 5–6 |
| A1 Poster design | CAD / Prototyping + Software Developer | Design A1 poster using Canva or Figma; include: problem, dataset, system architecture diagram, model results table, device photo, impact section | Day 7–14 |
| Live pitch deck preparation | Data Scientist + Software Developer | Build 10-15 minute presentation covering: problem, solution overview, demo, technical deep-dive, impact, and future work | Day 10–18 |
| Demo script & rehearsal | All team members | Script the live demo of both the mobile app and embedded device; rehearse full pitch 3+ times; prepare for judge Q&A | Day 15–21 |
| Summit Day — poster & live pitch | All team members | Attend Ghana AI Summit on 30th July 2026 in Accra; present poster, deliver live pitch, demonstrate both prototypes to judging panel | 30 Jul 2026 |

Stage Deliverables:

- Technical Abstract submitted by 1st July 2026

- A1 poster printed and ready for Summit Day

- Pitch deck finalised and rehearsed

- Both prototypes transported and demo-ready for 30th July

# Overall Responsibility Matrix

This matrix summarises each team member's primary involvement across all six development stages.

| Team Member | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | Stage 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Data Scientist (Lead) | Primary | Primary | Support | — | Support | Primary |
| Software Developer | Primary | Support | Primary | Primary | Primary | Support |
| Electronics Engineer | Primary | — | — | Primary | Primary | — |
| CAD / Prototyping | Primary | — | — | Primary | Support | Primary |
| Primary = leads and owns the task Support = contributes to the task — = not involved in this stage |  |  |  |  |  |

# Key Dates & Milestones

| Date | Milestone | Owner |
| --- | --- | --- |
| Now – Week 2 | Dataset prepared, GitHub set up, hardware procured | All |
| Week 5 | Trained model (.tflite) finalised and committed | Data Scientist |
| Week 8 | Mobile app (.NET MAUI) completed and tested | Software Dev. |
| Week 9 | Embedded device fully assembled and firmware deployed | Electronics + CAD |
| Week 10 | Integration testing complete, all bugs resolved | All |
| 1 Jul 2026 | Technical Abstract submitted (challenge deadline) | Data Scientist |
| 15 Jul 2026 | Shortlist notifications expected | — |
| Week 11–12 | Poster printed, pitch rehearsed, device packed | All |
| 30 Jul 2026 | Ghana AI Summit — poster + live pitch + demo | All |

CropSense  |  Ghana AI Innovation Challenge 2026  |  Kumasi Technical University